## Tracks
track_id | name | description | routing_rule | policy_citation | verification | verified_by | verified_on
cip | Capital Improvement Plan | 10-year School Board plan funding major facility investments largely through County GO bonds | Large building-system projects the School Board lists in the adopted CIP (Oakridge is here) | Va. Code § 15.2-2640 (bond referendum request); adopted FY2027-36 CIP | documented
mcmm | Major Construction/Minor Maintenance | Facility repair and replacement work funded outside the CIP; $3.0M one-time investment in FY27 per the APS budget page | Smaller facility work not listed as a CIP project; dollar cutoff vs CIP not found |  | draft
gift | Private gift / external funding | Donations or privately funded building/grounds improvements reviewed under D-15 | Any private money for a facility improvement; approver depends on project size | APS Policy D-15 External Funding (2025 draft text) | draft

## Stages
stage_id | track_id | order | name | decider | venue | typical_duration | basis | source_id
cip-direction | cip | 1 | CIP direction | School Board | School Board meeting |  | fact | cip-fy27-36
cip-proposal | cip | 2 | Superintendent's proposed CIP | Superintendent | School Board meeting information item |  | fact | cip-fy27-36
cip-adoption | cip | 3 | CIP adoption and bond request | School Board | School Board meeting (vote) |  | fact | cip-fy27-36
cip-county-ballot | cip | 4 | County Board resolution and court-ordered election | County Board then Circuit Court | County Board meeting |  | requirement | cip-fy27-36
cip-referendum | cip | 5 | Bond referendum | Arlington voters | General election | 1 day | fact | county-bond-2026
cip-design | cip | 6 | Project development and design | School Board approves at milestones | School Board meetings |  | estimate | cip-fy27-36
cip-construction | cip | 7 | Construction | APS Facilities and Operations | Site | Summer 2027 to 2029 for Oakridge | estimate | cip-fy27-36
mcmm-budget | mcmm | 1 | Annual MC/MM budget allocation | School Board | Budget adoption | annual | interpretation
mcmm-work | mcmm | 2 | Project selection and execution | APS Facilities and Operations | Staff |  | interpretation
gift-proposal | gift | 1 | Donor proposal to principal (2025 draft policy) | Principal | School |  | requirement | policy-d15-draft-2025
gift-staff-review | gift | 2 | Review by Asst. Supt. F&O and Superintendent (2025 draft policy) | Superintendent (or designee) | Staff review |  | requirement | policy-d15-draft-2025
gift-board | gift | 3 | School Board approval (projects >= $100,001) (2025 draft policy) | School Board | School Board meeting |  | requirement | policy-d15-draft-2025
gift-mou | gift | 4 | MOU (>= $15,000) or acceptance letter (< $15,000) (2025 draft policy) | School Board or Superintendent; principal for < $15000 |  |  | requirement | policy-d15-draft-2025

## Schools
school_id | name | district | status | notes
oakridge | Oakridge Elementary School | Arlington Public Schools | live

## Needs
need_id | school_id | title | category | summary | track_id | current_stage_id | stage_basis | stage_source_id | cost | cost_basis | cost_source_id | window | window_basis | window_source_id
oakridge-hvac | oakridge | Oakridge Elementary HVAC replacement | hvac | Replace aging HVAC equipment. The project is named in the proposed $80M school bond (Nov 3, 2026) as part of a broader Oakridge Refresh (HVAC, roofing, flooring, painting). | cip | cip-referendum | fact | county-bond-2026 | $31M (whole Refresh: HVAC, roofing, flooring, painting) | estimate | cip-fy27-36 | Summer 2027 to 2029 | estimate | cip-fy27-36

## Milestones
milestone_id | need_id | date | label | status | decider | venue | basis | source_id
oakridge-cip-adopted | oakridge-hvac | 2026-06-18 | School Board adopts FY2027-36 CIP including Oakridge HVAC replacement and $80M bond request | done | School Board | School Board meeting | fact | cip-fy27-36
oakridge-county-cip | oakridge-hvac | 2026-07-21 | County Board adopts County CIP containing the bond projects | done | County Board | County Board meeting | fact | county-bond-2026
oakridge-referendum | oakridge-hvac | 2026-11-03 | Voters decide $80M school bond (Question 4) incl. $31M Oakridge Refresh | next | Arlington voters | General election | fact | county-bond-2026
oakridge-construction-start | oakridge-hvac | 2027-06-01 | HVAC replacement implementation begins | later | APS Facilities and Operations | Site | estimate | cip-fy27-36
oakridge-complete | oakridge-hvac | 2029-01-01 | Implementation scheduled to end during 2029 (CIP planning estimate) | later | APS Facilities and Operations | Site | estimate | cip-fy27-36

## Engage
engage_id | need_id | venue | when | how | url | basis | source_id
oakridge-sb-comment | oakridge-hvac | School Board meeting public comment | Regular meetings, generally 7 p.m. at the Syphax Education Center | Online speaker form opens four business days before and closes 4 p.m. the day before; max 30 speakers x 2 minutes | https://www.apsva.us/arlington-school-board/school-board-meetings/sign-up-to-speak/ | requirement | aps-sign-up-to-speak
oakridge-ws-mcmm | oakridge-hvac | School Board work session on Facilities (Maintenance / Work Orders / MCMM) | 2026-09-29 1:00-2:30 p.m. | Observe | https://www.apsva.us/post/september-schedule-of-board-meetings-work-sessions-and-advisory-council-and-committee-meetings-4/ | fact | aps-sept-2026-schedule
oakridge-ws-fy28 | oakridge-hvac | School Board work session on FY 2028 Budget Direction | 2026-09-29 10:45 a.m.-12:15 p.m. | Observe | https://www.apsva.us/post/september-schedule-of-board-meetings-work-sessions-and-advisory-council-and-committee-meetings-4/ | fact | aps-sept-2026-schedule
oakridge-vote | oakridge-hvac | General election Question 4 | 2026-11-03 | Vote on the $80M school bond | https://www.arlingtonva.us/Government/Programs/Budget-Finance/Bonds/2026-Bond-Referenda | fact | county-bond-2026
oakridge-advisory | oakridge-hvac | APS advisory councils (2026-27) | Applications through 2026-10-31 | Apply to a new advisory council | https://www.apsva.us/post/september-schedule-of-board-meetings-work-sessions-and-advisory-council-and-committee-meetings-4/ | fact | aps-sept-2026-schedule

## Inquiries
inquiry_id | need_id | date | to | question | response_date | response_summary | status | source_id
email-2026-04-15 | oakridge-hvac | 2026-04-15 | Superintendent Durán | What is the plan to make my children's school safe for learning over the next two months? | 2026-04-16 | Copied the school principal, who will work closely to monitor the situation. | partial | email-2026-04

## Sources
source_id | title | publisher | url | retrieved_on | notes
cip-fy27-36 | APS Approved FY 2027-36 Capital Improvement Plan (CIP) | Arlington Public Schools | https://www.apsva.us/wp-content/uploads/sites/57/2026/08/APS-FY2027-36-CIP-REPORT-FINAL.pdf | 2026-09-24 | Adopted June 18 2026; report dated August 2026; Appendix C funding timeline is an image (not read)
aps-cip-approval-post | School Board Approves FY 2027-36 CIP Focused on School Renewal and Modernization | Arlington Public Schools | https://www.apsva.us/post/school-board-approves-fy-2027-36-cip-focused-on-school-renewal-and-modernization/ | 2026-09-24 | News post June 19 2026
aps-engage-cip | FY 2027-36 Capital Improvement Plan | Arlington Public Schools | https://www.apsva.us/engage/cip/ | 2026-09-24 | Lists Election Day as Nov 4 (conflicts with Nov 3 elsewhere)
county-bond-2026 | 2026 Bond Referenda | Arlington County Government | https://www.arlingtonva.us/Government/Programs/Budget-Finance/Bonds/2026-Bond-Referenda | 2026-09-24 | Question 4 text and project list
policy-d15-draft-2025 | Proposed revisions to Policy D-15 External Funding-Commercial Activities (draft) | Arlington School Board (BoardDocs) | https://go.boarddocs.com/vsba/arlington/Board.nsf/files/DD8P9T6391D5/$file/D-15%20External%20Funding-Commercial%20Activities.pdf | 2026-09-24 | January 2025 first draft; adopted text not verified
aps-budget-page | Budget | Arlington Public Schools | https://www.apsva.us/budget/ | 2026-09-24 | FY27 MC/MM $3.0M one-time; no definition
aps-superintendent | Superintendent's Office | Arlington Public Schools | https://www.apsva.us/departments/superintendents-office/ | 2026-09-24
aps-sign-up-to-speak | Speak at a School Board Meeting | Arlington Public Schools | https://www.apsva.us/arlington-school-board/school-board-meetings/sign-up-to-speak/ | 2026-09-24
aps-sept-2026-schedule | September Schedule of Board Meetings Work Sessions and Advisory Council and Committee Meetings | Arlington Public Schools | https://www.apsva.us/post/september-schedule-of-board-meetings-work-sessions-and-advisory-council-and-committee-meetings-4/ | 2026-09-24 | Posted Sep 2 2026
email-2026-04 | Email exchange with Superintendent Durán, April 15–16 2026 | Provided by team member (personal correspondence) |  | 2026-09-24 | Original held by the team; quoted in the pitch video.

## Legend
tab | column | meaning | allowed_values
Tracks | track_id | Short id for the track (lowercase-dashes)
Tracks | verification | Has an APS contact confirmed this track's stages and deciders? | draft ¦ documented ¦ confirmed
Stages | order | Position of the stage within its track (1 = first) | whole number
Stages | basis | What kind of claim the stage is | fact ¦ requirement ¦ estimate ¦ interpretation
Schools | status | live = every claim must have a source or the site will not build; draft = warnings only | live ¦ draft
Needs | current_stage_id | Must be a stage_id that belongs to the need's track_id
Needs | stage_basis / cost_basis / window_basis | What kind of claim each is | fact ¦ requirement ¦ estimate ¦ interpretation
Milestones | status | Exactly one milestone per need must be next | done ¦ next ¦ later
Milestones | date | ISO date | YYYY-MM-DD
Engage | basis | What kind of claim the venue is | fact ¦ requirement ¦ estimate ¦ interpretation
Inquiries | status | Did the authority answer the question? | answered ¦ partial ¦ unanswered
Sources | source_id | Referenced by every *_source_id column. Add the document here first.
(all) | *_id | Lowercase letters and digits and dashes only. No spaces.
(all) | blank cell | Leave blank when unknown. Never type TBD or ?.